## Project Planner
Project Timeline of Illuminati: The Game of Conspiracy
N = NOLAN, M = MATT, J = JOANNA |  |  |  | Plan Duration | [5 empty] | Actual Start
ACTIVITY | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Phase I: Ideas and Concept
Development Planning | N, M, J
Hardware Requirements | N, M, J
Software Requirements | N, M, J
Conceptual & Gameplay Discussion | N, M, J
Phase II: Development Timeline
Gantt Chart of Development Time |  | N, M, J
Phase III: Conceptual Development
Rules & Usecases |  |  | N, M, J
FlowCharts |  |  | N, M, J
Concept Art |  |  |  |  | M, J
Phase IV: Implementation & Debugging
Gameplay Rules, Testcases, and Functionality | [6 empty] | N, J, M
Art and Visual FX | [8 empty] | J
Main Menu | [9 empty] | N, M
Debugging | [6 empty] | N, M, J
Documentation & Credits | N, M, J
Phase V: Verification and Release
Verification of Functionality | [11 empty] | N, M, J
Verification of Documentation | [11 empty] | N
Finalization and Release | [12 empty] | N, M, J